## Sheet1
Project: Lofthus Frukt og Saft
Project start: 20-Apr-20
|  |  | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-08 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-12 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-10 | 2020-07-13 | 2020-07-20 | MON
Activity | Responsible | Duration | Week 1 | Week 2 | Week 3 | Fri | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Fri | Week 9 | Week 10 | Week 11 | Week 12 | Fri | Week 13 | Week 14 | 2020-07-27
PLANNING
Set up domain/server | project manager | 2 days | 2
Intellectual proprety overview | project manager | 3 days | 3
Set up sitemap | developer | 3 days | 3
Visit & interview for textual content | journalist | 3 days |  | 3
Take photos for website | journalist | 2 days |  | 2
Studio photos of products for e-comm | journalist | 2 days |  |  | 2
Design research | graphic designer | 5 days | 5
Market research | marketing specialist | 5 days | 5
Create a brand ID | marketing specialist | 8 days |  | 5 | 3
MEETING | project manager
CONTENT & DESIGN
Responsive layout mockup | developer/graphic designer | 5 days |  |  | 5
Create website skeleton | developer | 5 days |  |  |  |  | 5
E-comm section | developer | 15 days | [5 empty] | 5 | 5 | 5
Edit pictures | journalist | 5 days |  |  | 3 |  | 2
Create textual content | journalist | 8 days | [5 empty] | 5 | 3
Select visuals (typography, color palette, ect) | graphic designer | 8 days | [5 empty] | 3 | 5
Style tile | graphic designer | 3 days | [7 empty] | 3
Marketing | marketing specialist | 23 days |  |  |  |  | 5 | 5 | 5 | 5 | 3
MEETING | project manager
DEVELOPMENT
Homepage | developer | 2 days | [8 empty] | 2
Set up about section | developer | 2 days | [10 empty] | 2
Create contact page | developer | 2 days | [10 empty] | 2
CSS styling | developer/graphic designer | 12 days | [11 empty] | 5 | 5 | 2
Advertising strategies | marketing specialist | 8 days | [10 empty] | 5 | 3
Establish relations with similar businesses | marketing specialist | 8 days | [12 empty] | 5 | 3
MEETING
MODIFICATION PERIOD
Trademark application patentstyret | project manager | 3 days | [15 empty] | 3
Feedback and adapt | teamwork | 10 days | [15 empty] | 5 | 5
FINAL HANDOVER MEETING | project manager | 1 day | [17 empty] | 1
|  |  | 2020-05-18 | 2020-05-19 | 2020-05-20 |  | 2020-05-21 | 2020-05-22 | 2020-05-25 | 2020-05-26 | 2020-05-27 |  | 2020-05-28 | 2020-05-29 | 2020-06-01 | 2020-06-02 |  | 2020-06-03 | 2020-06-04 | 2020-06-05
E-COMMERCE BREAKDOWN | Developer | 3 weeks
Create juices options
Include product pictures
Redirect to wholesale
Add delivery options
Add pre-order options
Add payment options
Set up secure online payment
CONTACT PAGE BREAKDOWN | Developer | 2 days | 2020-06-15 | 2020-06-16
Add a contact form
Add contact info for wholesale
Add contact info for Ind. Customers